## Sheet1
Iteration Number | Planned Stories |  | Planned Tasks | Priority | Implemented
1 | 1.1 | Authentication (login) | Encrypt user password | Must | Yes
|  |  | Save user information | Must | Yes
| 1.2 | Track patient information | Create patient | Must | Yes
|  |  | Edit patient | Must | Yes
2 | 2.1 | Administrator assigns nurse to ward | Assign nurses to wards | Must | Yes
| 2.2 | Encrypt patient information | Encrypt patient information | Must | No
| 2.3 | Patient changes beds | Track rooms and beds | Should | Yes
|  |  | Assign patients to rooms and beds | Must | Yes
| 2.4 | Track nurse information | Create nurse | Must | Yes
|  |  | Edit nurse | Must | Yes
|  |  | Delete nurse | Should | Yes
| 2.5 | Admin or nurse can assign patient to a room | Permissions | Should | No
| 2.6 | New patients are placed in a priority queue | Place patients in a priority queue | Must | Yes
| 2.7 | Nurse can checkout patient | Add "In Hospital" checkbox | Must | Yes
| 2.8 | View patients in ward |  | Must | Yes
3 | 3.1 | Track patients information | Add validation of user input | Must | Yes
| 3.2 | Nurse checks in/out patients | Add validation of user input | Must | Yes
| 3.3 | Patients change bed | Add validation of user input | Must | Yes
| 3.4 | New patients are placed in a priority queue | Add validation of user input | Must | Yes
| 3.5 | A doctor or a head nurse can enter nurses' information | Implement permissions | Should | Yes
| 3.6 | Assign nurses to wards |  | Must | Yes
| 3.7 | Nurses can view information of the patients that they are in charge of | Implement permissions | Should | Yes
| 3.8 | A secretary can enter patients' information when they arrive | Implement permissions | Should | Yes
| 3.9 | An administrator assigns a nurse to a ward | Implement permissions | Should | Yes
| 3.1 | An administrator or a nurse assigns a patient to a room | Implement permissions | Should | Yes
| 3.11 | A doctor or a nurse can search for a patient | Implement permissions | Should | Yes
|  |  | Search for patients | Must | Yes
| 3.12 | View nurses in wards | Show ward names instead of numbers in the table | Must | Yes