## Sheet1
Iteration Number | Planned Stories |  | Planned Tasks | Priority | Implemented
1 | 1.1 | Authentication (login) | Encrypt user password | Must | Yes
|  |  | Save user information | Must | Yes
| 1.2 | Track patient information | Create patient | Must | Yes
|  |  | Edit patient | Must | Yes
2 | 2.1 | Administrator assigns nurse to ward | Assign nurses to wards | Must | Yes
| 2.2 | Encrypt patient information | Encrypt patient information | Must | No
| 2.3 | Patient changes beds | Track rooms and beds | Should | Yes
|  |  | Assign patients to rooms and beds | Must | Yes
| 2.4 | Track nurse information | Create nurse | Must | Yes
|  |  | Edit nurse | Must | Yes
|  |  | Delete nurse | Should | Yes
| 2.5 | Admin or nurse can assign patient to a room | Permissions | Should | No
| 2.6 | New patients are placed in a priority queue | Place patients in a priority queue | Must | Yes
| 2.7 | Nurse can checkout patient | Add "In Hospital" checkbox | Must | Yes
| 2.8 | View patients in ward |  | Must | Yes
3 | 3.1